## Financial Portfolio Model
This is an example of testing a financial portfolio with a monte |  | Year 1 |  |  |  | Income to Date | Return to Date
carlo simulation. See the comments in the cells for more |  |  | Opening balance | 100000
information. To start, run a new simulation by selecting |  |  | Rate of return |  | #NAME?
"Monte Carlo" -> "Run Simulation" from the menu. |  |  | Income (loss) | #NAME?
|  |  | Closing balance | #NAME? |  | #NAME? | #NAME?
Simulation Parameters
Year 2
Expected return | 7.93% |  | Opening balance | #NAME?
Standard deviation | 5.4% |  | Rate of return |  | #NAME?
|  |  | Income (loss) | #NAME?
Starting balance | 100000 |  | Closing balance | #NAME? |  | #NAME? | #NAME?
Average return | #NAME? | Year 3
| #NAME? |  | Opening balance | #NAME?
|  |  | Rate of return |  | #NAME?
Return Probability |  |  | Income (loss) | #NAME?
Return | Probability |  | Closing balance | #NAME? |  | #NAME? | #NAME?
10000 | #NAME?
12500 | #NAME? | Year 4
15000 | #NAME? |  | Opening balance | #NAME?
17500 | #NAME? |  | Rate of return |  | #NAME?
20000 | #NAME? |  | Income (loss) | #NAME?
22500 | #NAME? |  | Closing balance | #NAME? |  | #NAME? | #NAME?
25000 | #NAME?
27500 | #NAME? |  | Gross return |  |  | #NAME? | #NAME?
30000 | #NAME?
32500 | #NAME?
35000 | #NAME?
37500 | #NAME?
40000 | #NAME?
42500 | #NAME?
45000 | #NAME?
47500 | #NAME?
50000 | #NAME?
Note on B17: Charting Simuation Results: The chart shows the probability of reaching certain minimum returns. We use the SimulationInterval function in a table (hidden under the chart) to find the probability, over all iterations of the simulation, of reaching a particular value. If you run a simulation with 1000 iterations, for example, and the gross return value is greater than $25,000 in 800 of the trials, the chart will show an 80% likelihood of reaching at least $25,000. Try changing the simulation parameters (cells C9-C12) and re-running simulations to see the effect. To run a simulation, select "Monte Carlo" -> "Run Simulation" from the menu.
Note on C14: Average Return: The average return is calculated by running a Monte Carlo simulation, then taking the average value of cell L26 (gross return) over all iterations. To see it work, run a new simulation by selecting "Monte Carlo" -> "Run Simulation" from the menu.
Note on C15: Average Return: The average percent return is calculated by running a Monte Carlo simulation, then taking the average value of cell M26 (gross percent return) over all iterations.
Note on H26: Gross Return: The gross return is the total return over four years. This value is recalculated in each iteration, and is used as the basis for our analysis.
Note on J4: Random Rate of Return: The return in each period is randomly selected, using the parameters described at left. In each iteration of the simulation, a new random value is selected.
Note on L26: Gross Return: The gross return is the total return over four years. This value is recalculated in each iteration, and is used as the basis for our analysis.

## Project Planning Model
This is an example of a project planning spreadsheet using a monte carlo | [6 empty] | Simulation Results
simulation to find likelihood of completion within time estimates. To start,
run a new Monte Carlo simulation using the "Monte Carlo" menu. | [6 empty] | Probability of completion by "Most Likely" |  |  | #NAME?
[7 empty] | Probability of completion within 10% |  |  | #NAME?
Tasks |  | Completion Estimates (weeks)
Chart of completion probability
Group 1 |  | Minimum | Most Likely | Maximum | Sample | Average | Completion | Probability | Aggregate
| Task A | 2 | 6 | 8 | #NAME? |  | 15 | #NAME? | #NAME?
| Task B | 4 | 5 | 8 | #NAME? |  | 15.5 | #NAME? | #NAME?
| Task C | 4 | 7 | 8 | #NAME? |  | 16 | #NAME? | #NAME?
[7 empty] | 16.5 | #NAME? | #NAME?
| Total | 10 | 18 | 24 | #NAME? | #NAME? | 17 | #NAME? | #NAME?
[7 empty] | 17.5 | #NAME? | #NAME?
Group 2 | [6 empty] | 18 | #NAME? | #NAME?
| Task A | 8 | 12 | 20 | #NAME? |  | 18.5 | #NAME? | #NAME?
| Task B | 1 | 2 | 2 | #NAME? |  | 19 | #NAME? | #NAME?
[7 empty] | 19.5 | #NAME? | #NAME?
| Total | 9 | 14 | 22 | #NAME? | #NAME? | 20 | #NAME? | #NAME?
[7 empty] | 20.5 | #NAME? | #NAME?
Group 3 | [6 empty] | 21 | #NAME? | #NAME?
| Task A | 3 | 5 | 10 | #NAME? |  | 21.5 | #NAME? | #NAME?
| Task B | 2 | 7 | 9 | #NAME? |  | 22 | #NAME? | #NAME?
| Task C | 4 | 6 | 9 | #NAME? |  | 22.5 | #NAME? | #NAME?
[7 empty] | 23 | #NAME? | #NAME?
| Total | 9 | 18 | 28 | #NAME? | #NAME? | 23.5 | #NAME? | #NAME?
[7 empty] | 24 | #NAME? | #NAME?
Maximum |  | 10 | 18 | 28 | #NAME? | #NAME?
Note on E8: Minimum, Maximum and Most Likely: For each task, we obtain estimates of the completion time. Minimum and Maximum are also referred to as "Optimistic" and "Pessimistic" estimates. We use these values to select random values during the probability simulation, using the beta-PERT distribution. After the simulation is run, we use the generated random values to test the probability of completion by the estimated dates.
Note on H8: Sample Value: For each task, we select a random value, based on the given time estimates. When the probability simulation is run, this value will change for each iteration.
Note on H13: Total: The total is the total of our sample (random) values for each group.
Note on H29: Maximum Value: Since we want to find the completion time, we take the maximum time over the three groups. In a simulation, this value will change at each step; it is the basis for our analysis.
Note on K7: Probability Chart: The chart shows the likelihood of completion within certain ranges, as well as the aggregate (total) probability of completion by a certain time. The bars represent completion on the specified date using the SimulationInterval function (under the chart). The line represents the probability of completion on or before that date.
Note on O4: Probability: Over the probability simulation, taking new random values at each step, this is the probability that we will finish the task on or before the "most likely" estimate. It's based on the maximum sample value in cell H29.